## GRC Mapping
Ironbridge Health Alliance — Compliance & GRC Mapping
Mapping each technical control to the regulatory language auditors and executives use — HIPAA, NIST 800-53, NIST 800-66, CIS Controls
ID | Control Area | Technical Control | HIPAA Reference | NIST 800-53 | NIST 800-66 | CIS Control | Status | Date Planned | Date Implemented | Notes
GRC-001 | Network segmentation | VLAN isolation between corporate, clinical, and legacy segments | §164.312(a)(1) Access Control | SC-7 Boundary Protection | Access control safeguards | CIS Control 12 — Network Infrastructure Management | Planned | 2026-07-08
GRC-002 | Audit logging & monitoring | Wazuh centralized logging, alerting, FIM | §164.312(b) Audit Controls | AU-2, AU-6 | Audit controls implementation | CIS Control 8 — Audit Log Management | Planned | 2026-07-08
GRC-003 | Identity & access management | AD hardening, GPO baseline, trust scoping | §164.312(a)(2)(i) Unique User ID | AC-2, AC-6 | Person/entity authentication | CIS Control 5/6 — Account & Access Management | Planned | 2026-07-08
GRC-004 | Vulnerability management | Nessus scanning, patch cadence | §164.308(a)(1) Risk Analysis | RA-5 Vulnerability Scanning | Risk analysis & management | CIS Control 7 — Continuous Vulnerability Management | Planned | 2026-07-09
GRC-005 | Contingency planning | Backup and recovery design | §164.308(a)(7) Contingency Plan | CP-9, CP-10 | Data backup plan | CIS Control 11 — Data Recovery | Planned | 2026-07-09
GRC-006 | Transmission security | Encrypted remote access, MFA on VPN/admin access | §164.312(e)(1) Transmission Security | SC-8, IA-2 | Transmission security | CIS Control 6.5 — MFA for Remote Access | Planned | 2026-07-10
Living document — update Status, Date Implemented, and Notes as each control is built out during weekly progress.

## Summary
Progress Summary
Last updated | 2026-07-07
Total Controls | 6
Implemented | 0
In Progress | 0
Planned | 6
% Implemented | 0%