## Threat Model
Ironbridge Health Alliance — Threat Model
Documented, publicly known healthcare breach and ransomware patterns — not hypothetical scenarios
Threat ID | Scenario | Real-World Pattern It Reflects | Where It Lives in This Build | Related Risk ID
T-1 | Legacy trust abuse | Acquired-entity trust relationships used as a lateral movement path in M&A-driven breaches | HAWTHORNE.LOCAL → IRONBRIDGE.LOCAL trust | IHA-001
T-2 | Unpatched SMB / lateral spread | The 2017 WannaCry pattern — worm-style spread across an unpatched, flat network | Hospital clinical VLAN (VLAN 20) | IHA-002
T-3 | Missing MFA on remote access | Credential-based compromise of remote access without MFA, seen in multiple major recent healthcare breaches | FW01 VPN / remote admin access | IHA-003
T-4 | Kerberoasting on service accounts | Credential theft via weak Kerberos service account hygiene | OU=ServiceAccounts, IRONBRIDGE.LOCAL | IHA-004
T-5 | Weak backup/recovery posture | Ransomware impact amplified by inadequate backup strategy | Contingency planning control (see GRC Mapping) | IHA-005
T-6 | Host-level cross-VLAN forwarding | Hypervisor/virtualization host misconfiguration enabling a network segmentation bypass independent of firewall policy enforcement | KVM/QEMU host; virbr1/2/3 (VLANs 10, 20, 30) | IHA-006
Living document — add a new row each time a new threat scenario is designed into the build.

## Risk Register
Ironbridge Health Alliance — Risk Register
Tracking each risk from discovery through mitigation or verification — evidence of follow-through, not just findings
Risk ID | Risk | Site/System | Status | Likelihood | Impact | Date Identified | Date Resolved | Notes
IHA-001 | One-way AD trust exposes corporate forest to compromise via a less-hardened legacy domain | Hawthorne → Ironbridge trust | Open |  |  | 2026-07-06
IHA-002 | Flat clinical VLAN increases lateral movement risk between hospital systems | VLAN 20 (Hospital) | Open |  |  | 2026-07-06
IHA-003 | Remote administrative access lacks MFA | FW01 | Open |  |  | 2026-07-06
IHA-004 | Kerberos audit policy not yet configured; service accounts vulnerable to credential-theft techniques | IRONBRIDGE.LOCAL, ServiceAccounts OU | Open |  |  | 2026-07-06
IHA-005 | Backup and recovery strategy not yet defined or tested | All sites | Open |  |  | 2026-07-06
IHA-006 | Host (KVM/QEMU) is multi-homed across all VLANs with IP forwarding enabled, creating a theoretical risk of bridging traffic between segments and bypassing FW01 | KVM/QEMU host; virbr1/2/3 (all VLANs) | Verified - Not Exploitable | Low | High | 2026-07-06 | 2026-07-06 | Verified via iptables FORWARD/LIBVIRT_FWI/FWO/FWX chains: base policy DROP, explicit REJECT-all on virbr1-3, only same-bridge ACCEPT rules exist. FW01 remains sole inter-segment path. Recommend periodic re-verification after host OS/libvirt updates; consider explicit host-level DROP rules between virbr1/2/3 as future defense-in-depth.
Living document — update Status, Date Resolved, and Notes as each risk is mitigated or verified during the build.

## Summary
Progress Summary
Last updated | 2026-07-07
Total Risks | 6
Open | 5
Mitigated | 0
Verified - Not Exploitable | 1
% Resolved or Verified | 16.67%